NORTH WEST LEICESTERSHIRE DISTRICT COUNCIL

CORPORATE SCRUTINY COMMITTEE – 30tht September 2010

| Title of report | QUARTER 1 PERFORMANCE MANAGEMENT REPORT – CORPORATE DIRECTORATE & SERVICE TRANSFORMATION |
| --- | --- |
| Contacts | Councillor Annette Bridges 01530 564645 Annette.Bridges@nwleicestershire.gov.uk Councillor N Rushton 01530 412059 Nicholas.Rushton@nwleicestershire.gov.uk Chief Executive 01530 454545 christine.fisher@nwleicestershire.gov.uk Head of Service Transformation 01530 454579 louise.bennett@nwleicestershire.gov.uk |
| Purpose of report | This is the performance report for the first quarter (April-June) 2010/2011. The report provides members of the Corporate Scrutiny Committee with information on the performance and progress made against the Council Delivery Plan objectives, targets and National Indicators (NIs), plus specific actions from Service SMART Plan’s. |
| Strategic aims | The report addresses performance against one of the Council’s Strategic Aims of : Organisational Development |
| Implications: |  |
| Financial/Staff | The report contains summary performance data on financial management and staff management |
| Link to relevant CAT | The report links to the work of: Stronger CAT Risk and Business Continuity Group Corporate Procurement Group |
| Risk Management | Risk management is applicable to all areas of the Council’s statutory duties and service provision, and forms an important element of good governance. |
| Equalities Impact Assessment | N/A |
| Human Rights | No direct implications |
| Transformational Government | No direct implications |
| Consultees | Corporate Leadership Team |
| Background papers | (1) Council Delivery Plan 2010-2014 (2) Annual Performance Plan 2010-2011 (3) SMART Plans –2009-2012 (4) Change Control Documents - Copies of each are held by the Service Transformation Unit |
| Recommendations | IT IS RECOMMENDED THAT THE CORPORATE SCRUTINY COMMITTEE RECEIVES AND COMMENTS ON THE QUARTER 1 PERFORMANCE REPORT |

# 1.	Performance Summary

# 1.1	Corporate & Service Transformation Performance Summary

    - The performance within Service Transformation has been good with positive outcomes being achieved for the organisation, highlights being:

- The completion of the risk management performance framework

- The development of a shared Equalities service

- The continued facilitation of the shared Revenues and Benefits Services

1.1.2	Procurement have made realised the following savings in the first quarter:

- The cash collection contract is being awarded to commence on the 2nd August, savings for NW have been identified as £6,000 per annum; across the Leicestershire District savings were made of £69,000 per annum.

- Printing and Distribution collaborative tenders with Leicester City will deliver savings to NWLDC of around £23,000.

1.1.3	The performance team have successfully loaded all 2010/11 planning information from both the Council and is LSP partnership groups on the system.  Initial investigations are now taking place on the communication of performance messages.

1.1.4	Equalities are continuing with the work that is necessary for us to be accredited against the framework and the Councils initial peer review is scheduled for later in the calendar year.

1.1.5	Customer Services are continuing to support the development of the new website with the implementation of transactional services; in addition they have exceeded their target for responding to customer complaints by 2%.

1.1.6	Revenue & Benefits are continuing to perform and at the end of Q1 were up 1.4% on the Council Tax Collection Target.

1.1.7	The Legal team have performed against all their targets and have made considerable progress in the development of the shared service with Charnwood.

1.1.8	Overall the performance of the Corporate and Service Transformation team has been positive with real savings achieved already through procurement.  The progress against further savings is good and the targets set are likely to be achieved or exceeded.  Further work needs to be carried out with the Environment team in order to remove the unknown element of the programme plan, this work is currently taking place and it is anticipated that this will move the indicator showing Amber to Green for Quarter 2. And Corporately there has been progress in key areas, specifically in shared service developments and the completion of the Statement of Accounts.

2.	Performance Against Council Delivery Plan

2.1.1	The following chart shows the Q1 status of indicator measures attached to outcomes for each service within the Directorate, 	which are contained within the Council Delivery Plan 2010 - 2014.

2.1.2	The following chart shows the Q1 status of indicator measures attached to actions that are contained within the Council Delivery Plan 2010 – 2014, for the Service Transformation.

2.1.3	The following chart shows the Q1 status of milestones attached to actions for each service that are contained within the 	Council Delivery Plan 2010 – 2014, for Service Transformation.

2.1.4	Performance Against Service Delivery Plan

The following chart shows the Q1 milestone status for each service, identified within their Service Delivery Plan, excluding 	all Council Delivery Plan milestones.

Council Delivery Plan Performance Summary

  - Priority – Value for Money

- Increase value for money and provide a better understanding of what people get for their money

- Improve communications with communities/residents to build local trust and confidence

- Base services on local needs and expectations Improve overall satisfaction with the area and sense of belonging

- Look at alternative, cost-effective ways to deliver services

- Respond to resident issues quickly, transparently and fairly

| Outcome |
| --- |
| VFMO1 – Improved communications with communities, citizens and customers. |
| Action | Indicator | Owner | Annual Target | Actual | Status Q1 |
| STIA06 - To improve the availability of performance information to customers and communities | STPI09 - Evidence of use by communities and customers | Head of Service Transformation - Louise Bennett | 20% Increase on base line | Q4 | N/A |

| STIA06 - To improve the availability of performance information to customers and communities |
| --- |
| Quarter | Milestone | Progress | Status |
| Q1 10/11 | Establish scope of the information to share and potential communication channels | Researching examples of good practice with other LA's and external partners, to establish the appropriate channels and the scope of performance information to be made available for customers & communities. |  |
| Q2 10/11 | Implement phase 1 |  |  |
| Q3 10/11 | Review and amend according to customer feedback |  |  |
| Q4 10/11 | Implement phase 2 |  |  |

| Outcome | Indicator | Owner | Target | Actual | Status |
| --- | --- | --- | --- | --- | --- |
| VFM03 – Performance of the authority will go up, whilst cost will remain the same or go down. | NI179 - Value for money - total net value of ongoing cash-releasing value for money gains that have impacted since the start of the 2008-09 financial year (Annual) | Financial Planning Manager – Pritesh Padaniya | £666k | Reported in Q4 | N/A |
| Action | Indicator | Owner | Annual Target | Actual | Status – Q1 |
| STIA03 - Deliver procurement savings within the Housing Planned Improvement Savings. | STPI04 - Identify Savings of £200,000 of cash for reinvestment into the HRA | Head of Service Transformation - Louise Bennett | £200k | Q4 | N/A |
| STIA04 - Using the category lists to aggregate spend and there by improve value for money through combined spending. | STPI05 - Reduction in current prices paid against prices achieved for the appropriate quality. | Head of Service Transformation - Louise Bennett | £60,000 | Q4 | N/A |
| STIA05 - Project Management and Support of High Risk Projects | STPI06 - Deliver % of Savings as identified within the VFM Programme | Head of Service Transformation - Louise Bennett | 80% | Q4 | N/A |
|  | STPI07 - % of project RAG status's that are green |  | 80% | 48% |  |

| STIA03 - Deliver procurement savings within the Housing Planned Improvement Savings. |
| --- |
| Quarter | Milestone | Progress | Status |
| Q1 10/11 | Identify procurement strategy and identify KPI's for sustainable impact measurement | The Procurement Strategy for HPIP 2010-2015 has been agreed. The KPI's to measure the impact of sustainable procurement have been discussed on a generic basis and specifics will be identified by project |  |
| Q2 10/11 | Tender/Access contracts |  |  |
| Q3 10/11 | Meet the requirements of the HPIP programme |  |  |
| Q4 10/11 | Meet the requirements of the HPIP programme |  |  |

| STIA04 - Using the category lists to aggregate spend and there by improve value for money through combined spending. |
| --- |
| Quarter | Milestone | Progress | Status |
| Q1 10/11 | Identify categories | Catering Supplies Personal Protective Equipment Guarding/ Security Patrols have been identified as categories to investigate potential aggregation and savings |  |
| Q2 10/11 | Meet with relevant service managers to identify requirements |  |  |
| Q3 10/11 | Tender or identify frameworks |  |  |
| Q4 10/11 | Identify potential savings and amend supplier list to reflect work |  |  |

| STIA05 - Project Management and Support of High Risk Projects |
| --- |
| Quarter | Milestone | Progress | Status |
| Q1 10/11 | Deliver actions within the relevant programme and project plans |  | Red | Amber | Green | Unknown | TOTAL |  |
|  |  | Chief Executives |  |  | 2 |  | 2 |  |
|  |  | Community | 1 | 1 | 8 |  | 10 |  |
|  |  | Corporate | 1 | 2 | 3 |  | 6 |  |
|  |  | Environment | 1 | 1 |  | 7 | 9 |  |
|  |  | TOTAL | 11% | 15% | 48% | 26% |  |  |
| Q2 10/11 | Deliver actions within the relevant programme and project plans |  |  |
| Q3 10/11 | Deliver actions within the relevant programme and project plans |  |  |
| Q4 10/11 | Deliver actions within the relevant programme and project plans |  |  |

| Outcome | Indicator | Owner | Target | Actual | Status |
| --- | --- | --- | --- | --- | --- |
| VFM04 – Residents issues will be responded to quicker and in a transparent and fair manner. | CSPI06 - Improve response timescales for complaints received to meet 10 working day target. | Customer Service Manager - Matt Rockley | 80% | 82% |  |
| Action | Indicator | Owner | Annual Target | Actual – Q1 | Status – Q1 |
| STIA07 - Developing a comprehensive plan to improving the Councils performance against the equalities framework and as such delivering services that meet customers needs | STPI10 - Positive outcome from external peer review | Head of Service Transformation - Louise Bennett | Yes | Q4 | N/A |

| STIA07 - Developing a comprehensive plan to improving the Councils performance against the equalities framework and as such delivering services that meet customers needs |
| --- |
| Quarter | Milestone | Progress | Status |
| Q1 10/11 | Agree plan to achieve "achieving level" of the equalities framework | The action plan and the project timeline has been developed and updated to reflect the new date for the IDeA Peer assessment. The revised action plan and project timetable will be considered by the Strong CAT at their next meeting The Peer assessment is now due to take place in February 2011. |  |
| Q2 10/11 | Review EIA plan |  |  |
| Q3 10/11 | Review Equalities Policy/Strategy |  |  |
| Q4 10/11 | Deliver actions in associated plans |  |  |

3.0	Service Delivery Plan Performance Summary

3.1	Customer Services Summary

    - Customer Services key actions progress summary, contained within the Service Development Plan for quarter 1.

| Key Action | Owner | Milestone | Progress | Status |
| --- | --- | --- | --- | --- |
| CSIA08 Develop reactive and joined up services and procedures to facilitate migration to Partnership Hub | Customer Service Manager - Matt Rockley | Contribute to development of Hub proposal | Customer profiling exercise commenced. Survey formatted and in place. Web survey capability now procured to support partner data capture. |  |
| CSIA09 Develop service delivery through enhanced e-channel communications | Customer Service Manager - Matt Rockley | Work with services to identify which aspects of services can be delivered electronically | New transactional website is up and running. Review of enabling technology to determine what can be provided electronically underway under A2S programme |  |
| CSIA10 Provide services in locations identified as having the greatest need | Customer Service Manager - Matt Rockley | Identify areas with the greatest need or least representation. | This will form part of the data profiling in support of the Access to Services Programme. Details from the customer survey will be matched to data held in local knowledge. Areas having the greatest need have been established through the Customer Survey undertaken through the Facing The Financial Challenge. |  |
| CSIA11 Develop a single point of contact for all customer enquiries | Customer Service Manager - Matt Rockley | Continue investigation into shared customer service function of Housing and Corporate | Shared Customer Service function for Housing and Corporate now to be taken in alignment with Facing the Financial Challenge. |  |
| CSIA12 Develop opportunities for income generation through Customer Services | Customer Service Manager - Matt Rockley | Identify potential partners and income streams | Access to Services will provide opportunities for delivering Customer Facing services on behalf of partners. |  |
| CSIA13 Develop 24/7 service provision through the website | Customer Service Manager - Matt Rockley | Determine the capabilities of the transactional website | Website due for launch early July. Transactional elements have been included in spec. Details of specific functionality yet to be determined. |  |
| CSIA14 Develop mechanisms to capture Customer Satisfaction | Customer Service Manager - Matt Rockley | Develop satisfaction survey in line with best practice from NOSSBG | Satisfaction survey being developed through County Wide CSM group along guidelines set by National One Stop Shop Benchmarking Group. |  |
| CSIA15 Develop consistent Customer Insight reports and mechanisms. | Customer Service Manager - Matt Rockley | Undertake gap analysis to determine what details are required | Customer survey developed for Facing the Financial Challenge. To be rolled out across interested partners. |  |
| CSIA17 Review Complaints procedure in line with Ombudsman guidelines | Customer Service Manager - Matt Rockley | Document current process and system | Specification for complaints system formatted. Analysis of the system operated by Housing underway. Review of Ombudsman Process also underway. |  |

# 3.2	Performance Summary – Finance

3.2.1	Finance key actions progress summary, contained within the Service Development Plan for Quarter 1.

| Key Action | Owner | Milestone | Progress | Status |
| --- | --- | --- | --- | --- |
| FPIA13 Implementation of CHP at Hood Park. Implementation of energy efficiency programme for Council Offices | Property Asset Manager – Simon Harvey | N/A | Programme to commence in quarter 2. | N/A |
| FPIA15 Conduct review of delivery options for payroll and implement the preferred option | Financial Planning Manager – Pritesh Padaniya | Commence review | Options appraised. Site visits undertaken. CLT report produced. Agreement for Market testing. Spec to be produced and tender options Q2 |  |
| FPIA16 Continue to work with partners to deliver shared service for revs and bens | Head of Service Transformation - Louise Bennett | Complete review | The review of service delivery options for Revenues & Benefits has been completed with the recommended option being to become a full and active member of a Shared Service with Hinckley & Bosworth BC and Harborough DC. A report will go to Cabinet in August seeking member approval to continue with this project. |  |
| FPIA17 Continue to improve time taken to assess new claims and changes to Housing Benefit (NI181 = 12 days) | Financial Planning Manager – Pritesh Padaniya | Promote the One Day Promise and Benefits Take-up in Vision and other media | Promotional articles have been placed in local news letters, and Vision magazine. A review of the One Day Promise procedures is scheduled to take place on the 22nd July. Further promotion will be undertaken in the next quarter. |  |
| FPIA18 To improve information provided in Statement of Accounts | Financial Planning Manager – Pritesh Padaniya | Development of improvements | Statement of Accounts completed in accordance with the regulatory requirements. |  |
| FPIA19 Continue to work with CBC to deliver shared service for Property Services | Financial Planning Manager – Pritesh Padaniya | No quarterly action | Shared Services on-going and progressing well. |  |
| FPIA20 Implementation of IFRS | Financial Planning Manager – Pritesh Padaniya | Implementation of IFRS as per project plan | Discussions with District Auditor are ongoing re the classification of leases. Project on target. |  |
| FPIA21 Production of Statement of Accounts | Financial Planning Manager – Pritesh Padaniya | Production of SOA | Statement of Accounts completed – 24th June ‘10 |  |
| FPIA22 Undertake asset challenges on low performing Industrial Units. | Financial Planning Manager – Pritesh Padaniya | Agree asset challenges to be undertaken | Occupancy rate improved. |  |
| FPIA24 Timely issue of non payment reminders. Quarterly review of irrecoverable debts. Early action on defaulted payment plans. Prompt termination of services | Financial Planning Manager – Pritesh Padaniya | Issue of reminders / installment plans. | In line with agreed progress |  |

3.2.2	Finance performance indicators contributing to Key Actions within the Service Delivery Plan.

| Performance Indicator | Owner | Target | Actual | Status |
| --- | --- | --- | --- | --- |
| Finance |
| FPI16 - Council Tax Collection | Head of Service Transformation – Louise Bennett | 29.0% | 30.4% |  |
| FPI17 - NDR Collection | Head of Service Transformation – Louise Bennett | 30.0% | 29.0% |  |
| FPI19 - PPI 2A | Property Asset Manager – Simon Harvey | N/A | Q2 | N/A |
| FPI20 - Fully compliant by 31 March 2011 | Financial Planning Manager – Pritesh Padaniya | Yes | Q4 | N/A |
| FPI21 - By 30 June 2010 | Financial Planning Manager – Pritesh Padaniya | Yes | Yes |  |
| FPI22 - Unqualified opinion and publication by 30 September 2010 | Financial Planning Manager – Pritesh Padaniya | Yes | Q2 | N/A |
| FPI23 - All units make financial contribution to management costs | Property Asset Manager – Simon Harvey |  |  | N/A |
| FPI26 - Annual target of 25 sanctions | Head of Service Transformation – Louise Bennett | 7 | 12 |  |
| FPI27 - Reduction in arrears 1.5% | Head of Service Transformation – Louise Bennett | -1.5% | Q4 | N/A |
| FPI28 - Collection rate of 98% | Head of Service Transformation – Louise Bennett - | 98% | 98% |  |
| FPI29 - Reduction in Council Tax arrears 1.5% (annual target) | Head of Service Transformation – Louise Bennett | -1.5% | Q4 | N/A |
| NI181 - Time taken to process Housing Benefit/Council Tax Benefit new claims and change events (Quarterly) | Head of Service Transformation – Louise Bennett - | 13.0 | 11.4 |  |

# 3.3	Performance Summary – ICT

3.3.1	ICT key actions progress summary, contained within the Service Development Plan for Quarter 1.

| Key Action | Owner | Milestone | Progress | Status |
| --- | --- | --- | --- | --- |
| ICTIA13 Replace existing office telephone system with new VOIP system & extend Contact Centre capability to Housing Repairs | ICT Manager - Phil Clark | Finalise specification & procurement | Work on hold pending wide ranging review of ICT provision in the light of proposed move of Council Offices |  |
| ICTIA14 Review ICT Service provision | ICT Manager - Phil Clark | Implement recommendations | This has been deferred to 2010/11. |  |
| ICTIA15 Re-develop Council's main public website & the internal Intranet | ICT Manager - Phil Clark | Data gathering & collation | New web site live 1st July Intranet site live 1st July - further development of Sharepoint planned |  |
| ICTIA16 Implement mobile working for Building Control Service | ICT Manager - Phil Clark | Implement mobile working. | All technical elements of software & hardware in place & awaiting user training |  |
| ICTIA17 Review of Housing Service ICT facilities | ICT Manager - Phil Clark | Identify priorities & business cases | Initial review by consultancy Q2 completed by end of June. Further work required to determine priorities. |  |
| ICTIA18 Review ICT implications of EH Area based working | ICT Manager - Phil Clark | TBC38 | All milestones completed |  |
| ICTIA19 Implement video conferencing as part of County-wide scheme | ICT Manager - Phil Clark | Procurement of video conferencing | EU tender under way - assessment of tenders planned for Mid August |  |
| ICTIA20 Develop flexible working technologies | ICT Manager - Phil Clark | TBC43 | Final draft to be agreed April 2010. Consultation with customers and implementation Q1 2010/2011 |  |

# 3.4	Performance Summary – Human Resources

3.4.1	Human Resources key actions progress summary, contained within the Service Development Plan for Quarter 1.

| Key Action | Owner | Milestone | Progress | Status |
| --- | --- | --- | --- | --- |
| HRIA07 Supporting the Place Shaping Service with the Human Resources implications around the implementation of area working | Human Resources Manager - Mike Murphy | Support Project Plan. | Support has been provided to Directors and significant consultation has been undertaken. |  |
| HRIA08 Supporting the Housing Service with the Human Resources implications of a revised structure for 2011/12 to meet the changing needs of the service. | Human Resources Manager - Mike Murphy | NA | The timeframe for the review has subsequently been altered to 2012/13, so there is now no associated action required from HR at this time |  |
| HRIA09 Review and update the Housing Repairs and Maintenance Policy | Human Resources Manager - Mike Murphy | NA | Work is underway in the Department on this project but there are no HR issues at the present time. |  |
| HRIA10 Review travel to work data and implement measures to achieve in-year reductions. | Human Resources Manager - Mike Murphy | Complete data analysis report and suggest measures for reductions. | Some initial work has been completed on the data but this task is behind the original schedule. |  |
| HRIA11 Support services through VFM programme - options appraisal, labour costings, consultation, communication etc. | Human Resources Manager - Mike Murphy | Q1 According to VFM programme | HR support has been provided to a number of projects in the VFM programme in Q1. |  |
| HRIA12 Annual employee monitoring report developed and considered by CLT. | Human Resources Manager - Mike Murphy | Report to CLT. | Work has not commenced on this area by the end of Q1 due to staffing constraints. |  |
| HRIA13 Equality Impact assessment completed when policies are revised. | Human Resources Manager - Mike Murphy | TBC17 | No new or revised policies developed in Q1 so no Equality Impact Assessments undertaken. |  |
| HRIA14 To consider the equal pay implications of HR Pay and Reward policies. | Human Resources Manager - Mike Murphy | TBC21 | A number of HR Pay and reward policies have been considered during Q1. No significant changes have been made that warranted a review of potential equal pay implications. |  |
| HRIA15 Employee validation survey completed. | Human Resources Manager - Mike Murphy | Send out survey to all employees. | No progress has been made on this task during Q1 |  |
| HRIA16 Complete Local Labour market assessment | Human Resources Manager - Mike Murphy | TBC26 | No progress has been made on this task during Q1. |  |

# 3.5	Performance Summary – Legal & Democratic

3.5.1	Legal & Democratic key actions progress summary, contained within the Service Development Plan for Quarter 1

| Key Action | Owner | Milestone | Progress | Status |
| --- | --- | --- | --- | --- |
| LDIA09 Undertake an options appraisal for the service delivery of Internal Audit | Head of Legal and Democratic Services - Elizabeth Warhurst | Initiation | Project initiated and on track. Options are being explored with a view to taking an initial options appraisal to CLT on 27 July 2010. Savings target on track. VFM03 on track. |  |
| LDIA10 Use plain English in all election materials and committee papers and be conscious of the different formats that may be required (languages, font size etc) | Head of Legal and Democratic Services - Elizabeth Warhurst | Liaise with Angie Johnson, Neighbourhoods and Communities to identify local trends and groups. | Work is ongoing to ensure we capture all groups and update procedures and communications accordingly |  |
| LDIA11 Ensuring that all those affected by any proposals with the creation of new parishes are consulted and kept informed of the facts throughout each stage | Head of Legal and Democratic Services - Elizabeth Warhurst | Consult all interested parties on the draft proposals | The Re-Organisation Orders have been made following approval for the creation of parishes at Council in May. All interested parties were consulted. The Orders and associated maps are to be sent to all statutory bodies over the next few days. The Parishes come into effect 1st April 2011. |  |
| LDIA12 Assisting, as necessary, with the establishment of the new Parish Councils and working with the local people to explain the role of the parish councilor and encourage them to stand as candidates. | Head of Legal and Democratic Services - Elizabeth Warhurst | No action | Dates booked for event in January 2011 |  |
| LDIA13 Introduction of an electronic case management system | Head of Legal and Democratic Services - Elizabeth Warhurst | Consider technical implications of shared system | ICT have received a requisition order to purchase the hardware for the case management system. NWL & CBC are due to meet on 3rd August ’10 to agree the final solution for connectivity between the two sites. |  |
| LDIA14 Develop shared service arrangement | Head of Legal and Democratic Services - Elizabeth Warhurst | Approve business case | The business case has been approved by the management teams in both authorities and is due to go to the Cabinet meetings in July (CBC) and August (NWLDC). The phase 1 Joint Admin Structure is now out to consultation with affected staff and Unions and any comments will be fed into the Cabinet reports. |  |
| LDIA15 Support delivery of Transforming Services Programme as a member of the project 'experts panel' | Head of Legal and Democratic Services - Elizabeth Warhurst | Appointment to experts panel | Following the loss of the panels ‘expert’ from the legal team, a successful candidate has accepted the position and will commence work on 27th September 2010. Once in post he can be assigned to the experts’ panel, should this still go ahead? |  |
| LDIA16 Develop suite of standard contract documents for client use | Head of Legal and Democratic Services - Elizabeth Warhurst | Review requirements | The documents were created as part of the shared services toolkit and are now available on the intranet with the toolkit. |  |
| LDIA17 Develop Service Transformation/Shared Services toolkit | Head of Legal and Democratic Services - Elizabeth Warhurst | Complete and publish document on intranet | The documents have been produced and are now on the intranet on the Legal Services page. In addition the toolkit has been sold to CBC bringing in an income of £1,700. |  |

# 4.	Management of Absence – Corporate & Service Transformation

HR Management of Absence Quarter 1 (April - June) 2010/11

|  | Ave. No of FTE per Qtr |  | Number of Days Lost per Quarter | Cumulative |  | No of days lost per FTE |
| --- | --- | --- | --- | --- | --- | --- |
| Directorate | Q1 | Q2 | Q3 | Q4 |  | Q1 | Long | Short | Days lost (Q1+Q2+ Q3+Q4) |  | Q1 | Q2 | Q3 | Q4 |
| Corporate | 104.44 |  |  |  |  | 144.79 | 86.00 | 58.79 | 144.79 |  | 1.39 |  |  |  |
| All Directorates | 475.93 |  |  |  |  | 863.47 | 446.28 | 417.19 | 863.47 |  | 1.81 |  |  |  |

4.1	The proactive management of sickness absences with HR support has resulted in 3 home visits/sickness meetings being conducted and 2 HR supported return to work interviews completed.

4.2	Three employees have returned to work following long-term absences, of which 2 on managed phased returns.  Six HR supported return review/employee support meetings have been conducted in addition to line manager regular review meetings. Twenty nine return to work interviews have been completed and 1 attendance review meeting has been conducted.  One referral has been made to Occupational health and 1 to Access to Work.

4.3	Three risk assessments have been completed and adjustments made. 1 employee chose to resign because of their ill-health. Continued

4.4	The Corporate Directorate shows a slight increase in the average number of sickness days lost for quarter 1, compared to the same quarter in the previous year.  This increase is due to 3 long term absences, relating to major surgery, musculoskeletal injury and the final absentee chose to leave the authority during Q1 due to their ongoing medical condition.

- Financial Performance

  - Service Transformation

| SERVICE TRANSFORMATION - SUMMARY OF NET EXPENDITURE Quarter 1 |
| --- |
|  | ORIGINAL BUDGET | ORIGINAL BUDGET – Q1 | ACTUAL – Q1 | ORIGINAL EST VARIANCE – Q1 | FORECAST OUTTURN | FORECAST VARIANCE |
|  | EXP | INC | NET | EXP | INC | NET | EXP | INC | NET | EXP | INC | NET | EXP | INC | NET | EXP | INC | NET |
|  | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ |
| Head of Service | 300,410 | 300,410 | 0 | 71,950 | 0 | 71,950 | 61,397 | 0 | 61,397 | -10,553 | 0 | -10,553 | 296,840 | 300,410 | -3,570 | -3,570 | 0 | -3,570 |
| Project Management | 25,000 | 0 | 25,000 | 6,250 | 0 | 6,250 | -1,000 | 0 | -1,000 | -7,250 | 0 | -7,250 | 25,000 | 0 | 25,000 | 0 | 0 | 0 |
| Business Process Improvement | 5,000 | 0 | 5,000 | 1,250 | 0 | 1,250 | 5,600 | 0 | 5,600 | 4,350 | 0 | 4,350 | 5,600 | 0 | 5,600 | 600 | 0 | 600 |
| Equalities & Diversities | 10,000 | 0 | 10,000 | 2,500 | 0 | 2,500 | 0 | 0 | 0 | -2,500 | 0 | -2,500 | 10,000 | 0 | 10,000 | 0 | 0 | 0 |
| TEN | 7,000 | 0 | 7,000 | 1,750 | 0 | 1,750 | 530 | 0 | 530 | -1,220 | 0 | -1,220 | 7,000 | 0 | 7,000 | 0 | 0 | 0 |
|  | 347,410 | 300,410 | 47,000 | 83,700 | 0 | 83,700 | 66,527 | 0 | 66,527 | -17,173 | 0 | -17,173 | 344,440 | 300,410 | 44,030 | -2,970 | 0 | -2,970 |
| Salary costs included in above | 257,740 | 0 | 257,740 | 64,435 | 0 | 64,435 | 51,884 | 0 | 51,884 | -12,551 | 0 | -12,551 | 240,660 | 0 | 240,660 | -17,080 | 0 | -17,080 |

5.1.2	If expenditure continues at the current rate, Service Transformation supplies and 	services will be £2k overspent and transport costs £1k underspent.

5.2		Corporate Directorate Summary of Expenditure – Quarter 1 2010/11

|  | ORIGINAL BUDGET TO Q1 | ACTUAL TO Q1 | ORIGINAL EST VARIANCE Q1 | FORECAST OUTTURN | FORECAST VARIANCE |
| --- | --- | --- | --- | --- | --- |
|  | EXP | INCOME | NET | EXP | INCOME | NET | EXP | INCOME | NET | EXP | INCOME | NET | EXP | INCOME | NET |
|  | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ | £ |
| Corporate Director | 296,958 | 48,908 | 248,051 | 257,556 | 49,755 | 207,801 | -39,403 | 848 | -40,250 | 1,982,820 | 330,130 | 1,652,690 | -19,570 | 0 | -19,570 |
| ICT | 314,120 | 60,150 | 253,970 | 304,362 | 58,168 | 246,195 | -9,758 | -1,982 | -7,776 | 1,176,180 | 1,106,950 | 69,230 | 12,780 | -32,700 | 45,480 |
| HR | 65,787 | 0 | 65,787 | 63,238 | 0 | 63,238 | -2,549 | 0 | -2,549 | 303,810 | 222,080 | 81,730 | 940 | 0 | 940 |
| Customer Services | 101,506 | 26,813 | 74,694 | 116,418 | 26,762 | 89,656 | 14,912 | -50 | 14,962 | 476,840 | 450,040 | 26,800 | 20,700 | -4,650 | 25,350 |
| L & D Services | 349,596 | 6,413 | 343,183 | 318,621 | 9,738 | 308,883 | -30,975 | 3,326 | -34,300 | 1,674,950 | 1,259,260 | 415,690 | -48,170 | 3,430 | -51,600 |
| Finance | 10,302,573 | 5,828,678 | 4,473,895 | 3,059,610 | 6,175,961 | -3,116,351 | -7,242,962 | 347,284 | -7,590,246 | 26,249,280 | 25,670,400 | 578,880 | 1,115,850 | 1,190,890 | -75,040 |
| Holding Accounts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Whitwick Business Centre | 37,354 | 157,402 | -120,048 | 55,234 | 160,004 | -104,769 | 17,880 | 2,602 | 15,278 | 234,050 | 196,050 | 38,000 | -5,440 | -5,440 | 0 |
| TOTAL | 11,467,894 | 6,128,362 | 5,339,533 | 4,175,040 | 6,480,388 | -2,305,348 | -7,292,854 | 352,027 | -7,644,881 | 32,097,930 | 29,234,910 | 2,863,020 | 1,077,090 | 1,151,530 | -74,440 |

5.2.1	Summary of Underspend/Additional forecast income:

*	Salaries - Forecast £31k underspend due to vacant posts and reduced hours.

*	Customer Service Centre - There were £20k of savings built into the budget, £15.5k of these have been achieved by reduced hours.  The remainder is currently shown as an overspend.

*	Supplies & services budgets for Democratic Services and Electoral Registration are forecast to be £7k underspent

*	Members Allowances are forecast to be £10k underspent (allowances and supplies & services).

*	NDR costs for the Council Offices are forecast to be £11k less than budget, this is offset by an £8k fee from the rating agents (a percentage of the back dated refund in the 09/10 accounts).

*	Rental income from the industrial units is forecast to be £52k more than budget (providing occupancy remains at this level).

*	Benefits - Benefits costs are forecast to be £49k underspent.

*	Income from the Future Jobs Fund is forecast to be £14k

*	Investment income is forecast to be £20k more than budget

*	Post Office and Paypoint transactions are forecast to be £8k more than budget.

*	Audit Commission fees are forecast to be £4k underspent.

*	Insurance costs are forecast to be £4k underspent

5.2.2	Summary of Overspend/Reduced forecast income: -

*	Non Distributed Costs - £9.5k overspent.  This is the costs for Highfields St Depot and the closed public conveniences.*	Member Services

*	Printers and Print Room - £39k overspend.  There are additional costs for the rental of 2 servers and click charges due to higher usage.  Recharges are more on the printers and less on the Print Room due to changes in prices that have not yet been implemented.

*	Postage - £19k overspend (£12k postage costs, £2k operational equipment costs and £5k rental costs of a new machine to replace the machine we owned).

*	Revenues - income from summons costs is forecast to be £13k less than budget.

*	Rodent Control and bulky domestic waste concessions are forecast to be £14k overspent

*	There is £20k more redundancy costs in Exchequer Services than in the earmarked reserve to fund them.

5.3	Key Financial Indicators & Arrears

5.3.1	Performance against the key financial indicators and the current position on arrears are shown in the tables below.

| Key Financial Indicators | ANNUAL TARGET 10/11 | Q1 TARGET 10/11 | Q1 ACTUAL 10/11 | Q1 ACTUAL 09/10 |
| --- | --- | --- | --- | --- |
| FPI16 Collection of Council Tax | 97.7% | 29% | 30.4% | 30.5% |
| FPI17 Collection of Non Domestic Rates | 97% | 30% | 29% | 31% |

5.3.2	Business Rate Collection is currently below the TEN Targets, this is attributed to the recession and a ‘lag’ in payments from two large businesses that have undergone a reassessment of their Rateable Values. These payments are expected to come in later in the year.

6.	Project Performance against the Service Transformation Programme

| Directorate | Lead Officer | Service | 2010/11 | Milestones | Project on Track | Savings on Track against profile |
| --- | --- | --- | --- | --- | --- | --- |
| 001 | Chief Executives | Louise Bennett | Equalities | Q2 Initiation | A shared service has been agreed in principle by the Chief Executives for a District Wide Shared Equalities Service, | Yes | Status Red – 20K £20K |
| 004 | Community | John Richardson | Arts & Events | Q2 Decision and Implementation | Review in progress – final report due to Cabinet in October. | Yes | No profiled saving for 2011/12 |
| 003 | Community | John Richardson | Heritage & Museums (Grants) | Q2 Decision and Implementation | Review in progress – final report due to Cabinet in October. | Yes | Status Green – £ 4K |
| 004 | Community | Dave Halstead | Community Grants | Q2 Decision and Implementation | Review in progress – final report due to Cabinet in October. | Yes | Status Green £20K |
| 045 | Environment | Keith Fairbrother | Street Furniture | N/A | The timetable for when the service will be reviewed is currently under discussion. A paper detailing the strategic direction of each project was agreed at CLT. The projects will now be profiled into the core programme. | Unknown | Status Unknown –£6K |
| 007 | Environment | Sue Haslett | Building Control (Fee and Non Earning) | Q3 Decision | The original project time line will not be met, a review has taken place and the timeline for the decision has been moved to Q3. It is anticipated that the joint service will be in place for April 2011. The County Wide Project will be taken forward by the City Council as part of the Joint Change Programme. | No | Status Amber – £30K |
| 009 | Environment | Sue Haslett | Local Land Charges | Q2 Review | Awaiting further information from the Joint Change Programme – meetings of the project board have been cancelled so no further progress, priority is not currently being given to this project as there is no profiled saving associated with it. | No | No profiled saving for 2011/12 |
| 010 | Environment | Keith Fairbrother | Car Parking Incl. Enforcement and Street Enforcement | N/A | The timetable for when the service will be reviewed is currently under discussion. A paper detailing the strategic direction of each project was agreed at CLT. The projects will now be profiled into the core programme. | Unknown | No profiled saving for 2011/12 |
| 012 | Chief Executives | Caroline Richardson | Communication | Q1 Implement | The shared service has been implemented. | Yes | Status Green – £50K |
| 014 | Community | Sue Hallam | Housing Advice and Homelessness | Q1 Review | Completed | Yes | No profiled saving for 2011/12 |
| Directorate | Lead Officer | Service | 2010/11 | Milestones | Project on Track | Savings on Track against profile |
| 015 | Community | Sue Hallam | Housing Strategy and Enabling | Q1 Review | Completed | Yes | No profiled saving for 2011/12 |
| 018 | Community | Chris Lambert | Older Persons Service | Q2 Review | Currently the predicted timetable for the retendering exercise to commence is mid 2011. The Older persons service is still implementing the changes approved as part of the Options for Savings review, so limited progress with the initiation of this VFM project is anticipated before Q2. | Yes | No profiled saving for 2011/12 |
| 020 | Community | John Richardson | Leisure Centres | Q2 Decision | The process for market testing the leisure services is underway and on track. | Yes | No profiled saving for 2011/12 |
| 021 | Community | John Richardson | Sports Development and Physical Activity | Q1 Implement | Completed. | Yes | Yes in 10/11 |
| 022 | Community | Auzra Flynn | Community Safety | Q2 Implement | It was agreed at CLT on the 22nd June that a shared service with the police was the preferred option; this is being followed up by Dave Halstead. | No | No profiled saving for 2011/12 |
| 023 | Community / Environment | Dave Halstead | Neighbourhood & Community Management and Community Planning | Q2 Implement | A prolonged period of consultation has meant there has been slippage in the timescales so the project is now showing as amber. | No | No profiled saving for 2011/12 |
| 024 | Corporate | Alan Davis | Call Centre and Customer Services | Q2 Decision | Review is being informed by the Access to Service Project. Awaiting clarification of future scope. Project is also delayed by the telephony project. | No | Status Green – £20K saving to be found through other methods |
| 026 | Corporate | Andy Gough | Payroll | Q2 Review | Delay in tender process – which will now commence in August suggest that there may be a delay in implementation. Tender process to be fast tracked. |  | Status Amber – 25K |
| 028 | Corporate | Louise Bennett | Revenues and Benefits | Q2 Decision | Shared service review is being undertaken, the project is on timescale, but due to the increased performance that will be necessary for the timescale the associated saving will not be released until late 2011/12 and therefore will not contribute to savings for 2011/12. The project itself however remains on track. | Yes | Status Red – 30K |

| Directorate | Lead Officer | Service | 2010/11 | Milestones | Project on Track | Savings on Track against profile |
| --- | --- | --- | --- | --- | --- | --- |
| 031 | Corporate | Elizabeth Warhurst | Audit | Q1 Review | On Track | Yes | Status Green – £25K |
| 032 | Corporate | Elizabeth Warhurst | Democratic Services | Q2 Review | The member development project is in place – reassessment of member allowances and members budgets will be looked at in Autumn 2010 for implementation post elections in 2011. | Yes | No profiled saving for 2011/12 |
| 033 | Corporate | Elizabeth Warhurst | Legal | Q1 Implement | Progress is now happening and phase 1 is complete. A projected saving of 17K is in place with potentially more available – the profiled saving of 17K has meant that the project is amber rather than green. | Yes | Status Red – £35K |
| 034 | Environment | Kathryn Preece | Whole Service Environmental Health Review | N/A | The timetable for when the service will be reviewed is currently under discussion. A paper detailing the strategic direction of each project was agreed at CLT. The projects will now be profiled into the core programme. | Unknown | No profiled saving for 2011/12 |
| 036 | Environment | Sue Haslett | CCTV | N/A | The timetable for when the service will be reviewed is currently under discussion. A paper detailing the strategic direction of each project was agreed at CLT. The projects will now be profiled into the core programme. | Unknown | No profiled saving for 2011/12 |
| 040 | Environment | Keith Fairbrother | Waste, Grounds Maintenance, Cleansing, Parks, Open Spaces, Toilets | N/A | The timetable for when the service will be reviewed is currently under discussion. A paper detailing the strategic direction of each project was agreed at CLT. The projects will now be profiled into the core programme. | Unknown | No profiled saving for 2011/12 |
| 041 | Environment | Keith Fairbrother | Land Drainage & Flood Prevention | N/A | The timetable for when the service will be reviewed is currently under discussion. A paper detailing the strategic direction of each project was agreed at CLT. The projects will now be profiled into the core programme. | Unknown | No profiled saving for 2011/12 |
| 042 | Environment | Keith Fairbrother | Vehicle Maintenance | N/A | The timetable for when the service will be reviewed is currently under discussion. A paper detailing the strategic direction of each project was agreed at CLT. The projects will now be profiled into the core programme. | Unknown | No profiled saving for 2011/12 |

7.	Health & Safety Monitoring

7.1	Training

Due to the elections, no training sessions have taken place this quarter. But extra dates have been added to the original calendar.

7.2	Accidents

There has only been 1 reported accident in the Corporate Directorate, 	which relates to the Cleaning trade.

7.2.1	Quarterly meetings are held at Service, Directorate & Executive level, to discuss 	reported accidents and to establish preventive measures to be actioned.